## tasks
week 1
setup a project
SETUP ci/cd
installation
work with shared drive
admin panel
account create/restore password
week 2
save account data on the shared drive
first 16 slides templates
first 16 slides implementation
blue buttons (explanation) implemetation
week 3
images file settings
audio implementation
audio file settings
right conner counter with microphones implementation
week 4
game 1 without and with timer
implementation of how I am feeling progress bar
implementation of how I am feeling admin panel statistics
week 5
create a system to updatet the game text and answers
game 1 file settings
slides 20 -26 implementation
game 2
game 2 file settings
week 6
slides 29 - 35 templates
slides 29 - 35 implementation
slides 35 - 55 implementation
game 3
game 3 file settings
week 7
slides 61 - 64 implementation
game 4
game 4 file settings
slides 67 - 79 implementation
game 5
game 5 file settings
week 8
game 6
game 6 file settings
game 7
game 7 file settings
game 8
game 8 file settings
game 9
game 9 file settings
week 9
game 10
game 10 file settings
final text and pdf download
Swear words must not be allowed
week 10
license
license generator